HADDIYA

BACKEND × ZID INTEGRATION

Backend Development Roadmap

Module-wise Integration Plan with ZID Platform

| Document Scope | Backend Services + ZID Platform Integration |
| --- | --- |
| Frontend Status | Already designed and built (out of scope here) |
| Prepared for | Executive Leadership, Engineering, Stakeholders |
| Version | 1.0 |
| Date | June 2026 |

# Table of Contents

1. Project Scope & ZID Platform Overview

2. Integration Architecture & Principles

3. Backend Development Timeframe

4. Team Composition (Backend-Only)

5. Module-wise ZID Integration Plan

6. Phase-wise Delivery Plan

7. Technical Architecture Stack

8. Risk Analysis

9. Final Recommendation

# 1. Project Scope & ZID Platform Overview

## 1.1 Backend Scope

Haddiya backend is the orchestration and intelligence layer sitting between the consumer apps (already designed and built in React + React Native) and the ZID e-commerce platform. ZID — the leading Saudi multi-tenant commerce platform — provides the core commerce primitives (catalog, orders, customers, payments, shipping). Haddiya backend extends ZID with multi-vendor marketplace logic, the Gift AI Assistant, send-as-gift workflows, scheduled delivery, loyalty, vendor portal APIs, and admin operations — all the differentiators that ZID alone does not provide out of the box.

## 1.2 Why ZID?

ZID is purpose-built for the GCC market with native support for Mada, STC Pay, Tabby, Tamara, Apple Pay, Arabic-first storefront APIs, local shipping carriers (SMSA, Aramex, Naqel), and PDPL-compliant data residency. Building Haddiya on ZID compresses 4–6 months of commerce primitives work and inherits proven payment and tax flows. Haddiya focuses engineering effort on the high-value differentiators — multi-vendor orchestration, AI, and the gifting experience.

## 1.3 Business Objectives

| # | Objective | Target |
| --- | --- | --- |
| 1 | Use ZID for commerce primitives, focus team on differentiators | Save 4–6 months of build time |
| 2 | Webhook-driven near-real-time sync across all entities | Sync lag < 5s p95 |
| 3 | Idempotent integration that survives ZID API outages | Zero duplicate orders, zero lost webhooks |
| 4 | Vendor payout accuracy across multi-vendor splits | Reconciliation variance < 0.1% monthly |
| 5 | Backend SLA suitable for marketplace volumes | 99.95% uptime, p95 API latency < 250 ms |

## 1.4 Backend System Components

| Component | Description |
| --- | --- |
| ZID Platform | Catalog, orders, customers, payments, shipping (system-of-record) |
| Haddiya BFF | REST + GraphQL gateway for mobile/web; routes to ZID and internal services |
| ZID Connector Service | Typed SDK wrapper, OAuth token mgmt, rate-limit handling, retries |
| Webhook Ingestion Service | Receives ZID events, validates HMAC, dispatches to internal queues |
| Catalog Cache Service | PostgreSQL + OpenSearch mirror of ZID products + categories |
| Multi-Vendor Orchestrator | Maps Haddiya carts to per-vendor ZID orders; payout split logic |
| Gift AI Service | LLM + pgvector embeddings; product recommendation API |
| Gift Experience Service | Message cards, scheduled delivery, recipient mgmt, gift wrapping |
| Loyalty Ledger | Points earn/redeem, tier rules, ZID coupon bridge |
| Vendor Portal API | Per-vendor scoped APIs built on top of ZID per-store endpoints |
| Admin Operations API | Approvals, disputes, refunds (proxied to ZID) |
| Notification Service | Push (FCM/APNs), WhatsApp Business, transactional email |
| Reporting Service | Data warehouse (Snowflake/BigQuery) fed from ZID + Haddiya ledger |
| Platform Foundation | PostgreSQL, Redis, OpenSearch, SQS, S3, CloudFront, WAF |

# 2. Integration Architecture & Principles

Haddiya backend sits between the consumer apps and ZID. ZID is the system-of-record for all commerce primitives; Haddiya extends with marketplace, AI, and gifting logic. Six principles guide every integration decision:

| Principle | Description |
| --- | --- |
| ZID owns commerce primitives | Products, orders, payments, shipping, customers live in ZID as system-of-record. Haddiya never duplicates them as writeable. |
| Haddiya caches for performance | ZID data mirrored to PostgreSQL + OpenSearch for fast queries, AI ranking, and reporting. Cache invalidated via ZID webhooks. |
| Haddiya owns differentiators | Multi-vendor mapping, Gift AI, scheduled delivery, message cards, loyalty ledger, vendor payout tracking — Haddiya tables only. |
| Webhooks-first sync | Real-time consistency via ZID webhooks; periodic reconciliation as safety net (every 15 min for inventory, hourly for orders). |
| API contract isolation | Mobile/web apps call Haddiya BFF, never ZID directly. Lets us swap ZID later without touching clients. |
| Idempotent everything | Every ZID write (order create, refund, customer update) is idempotent with deterministic external_id to survive retries. |

## 2.1 High-level Data Flow

Consumer App  →  Haddiya BFF  →  Haddiya Services  ↔  ZID Connector  ↔  ZID Platform

Reads: Mobile/web → BFF → Haddiya cache (Postgres + OpenSearch); cache hydrated from ZID via webhooks.

Writes: Checkout, refunds, customer updates → Haddiya services → ZID API (with idempotency keys).

Events: ZID webhooks → ingestion service → SQS → consumer workers (cache, ledger, notifications).

Cron / safety net: Periodic reconciliation jobs catch any webhook misses.

# 3. Backend Development Timeframe

Frontend is already designed and built. These estimates cover backend services + ZID integration only. Buffer (~15%) included.

| Release | Scope | Weeks | Months | Notes |
| --- | --- | --- | --- | --- |
| Backend MVP | ZID account, OAuth, catalog sync, order orchestration, single-vendor checkout, single payment, basic webhooks | 8–10 | 2–2.5 | Pilot with 5–10 vendors |
| Backend V1 Production | Multi-vendor splits, full payment mix, send-as-gift backend, scheduled delivery, vendor portal API, admin API, Gift AI v1, full notifications | 16–20 | 4–5 | Public launch, ZID partner app live |
| Backend V2 Enterprise | Multi-country (UAE/Bahrain ZID stores), loyalty ledger, B2B gifting API, advanced analytics, anomaly detection, multi-warehouse | 28–34 | 7–8.5 | GCC expansion, enterprise SLAs |
| End-to-end (overlapped) | Phases run in parallel after MVP foundation | ~26 | ~6.5 | Backend complete with frontend already in place |

Total cumulative duration (sequential): ~24 weeks / 6 months.

With parallel pods: ~22 weeks / 5 months to V1 production.

# 4. Team Composition (Backend-Only)

## 4.1 Recommended V1 Backend Team

| Role | HC | Engagement | Duration | Notes |
| --- | --- | --- | --- | --- |
| Backend Lead / Architect | 1 | Full-time | Full project | Owns ZID integration design, code review |
| Backend Engineers | 3 | Full-time | Full project | ZID SDK, sync pipelines, vendor services |
| AI / ML Engineer | 1 | FT Phase D, PT after | ~3 months | Gift AI Assistant, embeddings |
| Data Engineer | 1 | PT (50%) from Phase F | ~2 months | Analytics pipeline, warehouse |
| DevOps / Platform Engineer | 1 | Full-time | Full project | IaC, CI/CD, observability, on-call |
| Security Engineer | 1 | Part-time (40%) | From Phase B | OWASP, secrets, pen test |
| QA / Integration Engineer | 1 | Full-time | From Phase B | API contract tests, ZID sandbox QA |
| Product Manager | 1 | Full-time | Full project | Roadmap, vendor liaison, ZID partner mgmt |
| Tech Project Manager | 1 | Full-time | Full project | Ceremonies, risk, ZID dependency tracking |
| Peak Total | ~9–10 FTE | — | — | Backend-only — frontend already complete |

## 4.2 Three Team Size Options

Backend can ship with a smaller team over a longer timeline. Three viable configurations:

| Option | Team Size | V1 Timeline | Composition | Tradeoff |
| --- | --- | --- | --- | --- |
| Lean (Solo Founder) | 5–6 FTE | 7–8 months | Sole BE lead + 2 BE + 1 DevOps + 1 QA + fractional Sec/AI | Slower, sequential, no AI until later |
| Standard (Recommended) | 9–10 FTE | 5 months | Full pod with dedicated AI, Data, Sec | Balanced; on-time backend launch |
| Aggressive | 13+ FTE | 3.5–4 months | Double backend pod, dedicated infra team | Coordination tax, diminishing returns |

Honest take:

9–10 FTE is right-sized for delivering full backend V1 in 5 months with parallel pods. If budget or hiring is constrained, the Lean 5–6 FTE option ships the same scope in 7–8 months by removing parallelism and deferring AI/Data work to later phases.

# 5. Module-wise ZID Integration Plan

Each module shows what ZID provides natively, where Haddiya adds custom logic, and the effort in person-weeks (PW). Complexity reflects integration risk, not raw size.

| # | Module | Description | ZID Coverage | Custom Effort | PW | Resources |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | ZID Partner App Registration | Register Haddiya as ZID partner app, scopes, OAuth credentials, sandbox + prod env config | Full (provided by ZID) | Config + flow wiring | 2 | 1 BE Lead |
| 2 | OAuth 2.0 Store Connection | Per-vendor store authorization, token storage (Secrets Manager), refresh handling | Native OAuth flow | Token vault + refresh worker | 4 | 1 BE, 1 Sec |
| 3 | ZID SDK / Connector Library | Typed NestJS client wrapping ZID REST API: retry, rate-limit aware (429 backoff), circuit breaker, request signing | REST endpoints only | All client logic in-house | 6 | 1 BE |
| 4 | Webhook Ingestion Service | Receive ZID events (order.created, product.updated, customer.created, etc.), HMAC verify, idempotency, SQS dispatch | Webhook delivery only | Full ingestion + dedupe | 8 | 1 BE |
| 5 | Catalog Sync Pipeline | ZID products → PostgreSQL + OpenSearch. Initial backfill + delta via webhooks. Bilingual fields, variants, media URLs | Products API (read) | Cache + reconciliation | 10 | 1 BE |
| 6 | Inventory Sync | Real-time stock from ZID + reservation hold during checkout. 15-min reconciliation job | Stock webhook + API | Reservation layer + recon job | 6 | 1 BE |
| 7 | Customer Sync | Mobile-first auth (phone+OTP) → ZID customer profile. Address book sync, GDPR/PDPL controls | Customer API | Auth bridge + privacy controls | 8 | 1 BE, 1 Sec |
| 8 | Cart & Pricing Service | Multi-vendor cart, ZID pricing rules (tax, promotions), Haddiya-applied platform discounts | Cart API per store | Cross-store aggregation | 10 | 1 BE |
| 9 | Order Orchestration | Haddiya checkout → 1..N ZID orders (one per vendor). Saga pattern for partial failures. Order status aggregation to customer | Order create API + webhooks | Saga + state machine | 14 | 1.5 BE |
| 10 | Payment Integration via ZID | Leverage ZID gateway abstraction (Mada, STC Pay, Tabby, Tamara, Apple Pay, COD). 3DS handled by ZID | Full PSP coverage | Checkout glue + retry | 6 | 1 BE, 1 Sec |
| 11 | Shipping & Carrier Integration | ZID carriers (SMSA, Aramex, Naqel) + Haddiya scheduled delivery windows stored as order metadata | Native carrier integrations | Schedule layer + tracking | 8 | 1 BE |
| 12 | Refunds & Returns API | Initiate refund in ZID, sync vendor payout ledger, notify customer | Refund API | Payout reconciliation | 6 | 1 BE |
| 13 | Multi-Vendor Mapping Service | Map Haddiya vendor → ZID store/sub-store. Vendor lifecycle (active, suspended, pending KYC) | ZID Marketplace plan or 1 store/vendor | Mapping + RBAC | 12 | 1 BE |
| 14 | Vendor Payout Ledger | Track commission per order, split calc, payout schedule. Reconciles to ZID order totals daily | Order totals from ZID | Full ledger in Haddiya | 12 | 1 BE, finance review |
| 15 | Vendor Onboarding API | KYC document upload (S3), approval workflow, ZID store provisioning via ZID admin API | Store provisioning API | KYC + approval flow | 10 | 1 BE, ops |
| 16 | Vendor Portal API | Per-vendor scoped: products, orders, earnings, payouts. Built on ZID per-store APIs with Haddiya RBAC layer | ZID Products + Orders APIs | RBAC + earnings calc | 14 | 1 BE |
| 17 | Gift AI Assistant Service | LLM + product embeddings (pgvector). Queries Haddiya catalog cache, never ZID directly | None (Haddiya-only) | Full build | 12 | 1 AI, 1 BE |
| 18 | Send-as-Gift Backend | Message cards (templates), recipient details, gift wrapping options. Attached to ZID order via custom fields/metadata | Order metadata fields | Gift entity + assets | 8 | 1 BE |
| 19 | Scheduled Delivery Logic | Date/time window selection, vendor capacity check, carrier handoff timing | Order metadata | Slot mgmt + validation | 6 | 1 BE |
| 20 | Promotions & Coupons Bridge | Haddiya platform coupons + ZID native discounts. Stacking rules, eligibility validation | ZID discount API | Bridge + stacking logic | 8 | 1 BE |
| 21 | Loyalty & Points Ledger | Earn on completed orders (ZID webhook), redeem via ZID coupon mint. Tiering rules | ZID coupon API | Full ledger + tiers | 10 | 1 BE |
| 22 | Notifications Service | Push (FCM/APNs), WhatsApp Business, transactional email (SES). Subscribes to ZID order webhooks | Webhook events | All channels in-house | 10 | 1 BE |
| 23 | Admin Operations API | Vendor approvals, dispute resolution, manual refunds, catalog moderation. Proxies to ZID where applicable | Admin endpoints | Workflow layer | 10 | 1 BE |
| 24 | Reporting & Analytics Pipeline | ETL from ZID Orders API + Haddiya ledger → Snowflake. GMV, AOV, vendor performance, cohort retention | Orders/Customers APIs (export) | Full DW + dashboards | 12 | 1 Data, 1 BE |
| 25 | Document Management Service | Vendor KYC, invoices (ZID provides), gift card art templates. S3 + signed URLs | Invoice generation | KYC + asset storage | 4 | 1 BE |
| 26 | Customer Support API | Ticket flow, order lookup (ZID), refund actions, chat handoff (Zendesk/Intercom) | Order/refund APIs | Ticket layer | 6 | 1 BE |
| 27 | Auth & RBAC | Haddiya users (customer/vendor/admin) — separate identity from ZID. JWT, refresh, MFA for vendors | ZID customer auth (consumer side) | Vendor/admin IdP + RBAC | 8 | 1 BE, 1 Sec |
| 28 | Rate-Limit & Quota Mgmt | Stay within ZID API quotas (per-store + per-app). Distributed token bucket via Redis | ZID rate-limit headers | Quota orchestration | 5 | 1 BE |
| 29 | Observability & Tracing | Track ZID API latency, webhook delivery success, retry counts. OpenTelemetry traces span Haddiya → ZID | ZID returns request IDs | Full instrumentation | 8 | 1 DevOps |
| 30 | Security & Compliance | OWASP, PDPL, GDPR. ZID OAuth token vault, webhook HMAC, PII encryption at rest | ZID handles PCI scope | Haddiya-side hardening | 10 | 1 Sec, DevOps |
| 31 | DevOps & Infrastructure | IaC (Terraform), CI/CD (GitHub Actions), ECS/EKS, env separation (dev/stage/prod), DR strategy | — | Full build | 14 | 1 DevOps |
| 32 | Disaster Recovery & ZID Outage Playbook | Read-only mode when ZID down, queued writes, customer messaging, auto-replay when ZID recovers | — | Full design + drills | 6 | 1 DevOps, 1 BE |

Total: ~273 person-weeks across 32 modules.

# 6. Phase-wise Delivery Plan

## Phase A — ZID Foundation · Weeks 1–4

ZID partner app registration, OAuth credentials, sandbox environment.

ZID API contract review, scope definition, rate-limit budget.

Connector SDK skeleton (NestJS), authentication flow, retry/backoff.

Webhook ingestion service, HMAC verification, SQS dispatch.

PostgreSQL schema for cache, multi-vendor mapping, ledger tables.

Initial CI/CD pipeline, staging environment with ZID sandbox.

Deliverables: Working OAuth flow, webhook ingest, ZID SDK v0.1, staging env.

## Phase B — Core Commerce Sync · Weeks 4–10

Catalog sync (products, categories, variants) → PostgreSQL + OpenSearch.

Inventory sync via webhooks + 15-min reconciliation.

Customer sync (Haddiya auth → ZID customer profile).

Cart and pricing service (single-vendor first).

Order orchestration v1 (single-vendor checkout, ZID order create, webhook listener).

Payment integration via ZID gateway (Mada + COD initially).

Deliverables: End-to-end single-vendor purchase flow on staging. Webhook reliability > 99%.

## Phase C — Multi-Vendor Layer · Weeks 8–14

Vendor onboarding API + KYC workflow + ZID store provisioning.

Multi-vendor mapping service.

Cart splitting → N ZID orders, saga for partial failures.

Vendor payout ledger + daily reconciliation against ZID totals.

Vendor Portal API (products, orders, earnings scoped per vendor).

Deliverables: Two vendors transacting in parallel, accurate payout split.

## Phase D — Differentiator Modules · Weeks 12–18

Gift AI Assistant: embeddings pipeline, LLM-backed recommendation API.

Send-as-gift backend (message cards, recipient details, wrapping).

Scheduled delivery slot mgmt + carrier handoff timing.

Loyalty ledger + ZID coupon bridge for redemption.

Promotions bridge (Haddiya coupons + ZID discounts, stacking rules).

Deliverables: AI-driven recommendations live; gifting metadata flowing end-to-end.

## Phase E — Operations & Ops APIs · Weeks 14–20

Admin Operations API (approvals, disputes, refunds).

Notifications service (push, WhatsApp, email) wired to ZID webhooks.

Customer support API + ticketing integration.

Refund and return flow with payout reconciliation.

Deliverables: Full admin workflows; ops team can manage vendors and orders without ZID UI.

## Phase F — Analytics & Hardening · Weeks 16–22

Reporting pipeline: ZID → Snowflake/BigQuery; Looker dashboards.

Observability: OpenTelemetry traces, Datadog APM, RUM, error tracking.

Security hardening: pen test, OWASP review, secrets rotation drill.

Disaster recovery playbook + ZID outage simulation.

Performance: k6 load tests at 5× expected peak.

Deliverables: Production-ready, monitored, security-cleared backend.

## Phase G — Production Launch & Stabilization · Weeks 20–24

Production cutover, blue-green deploy.

On-call rotation, status page.

Pilot vendor cohort (10–15) on production.

Tuning based on real-traffic metrics.

Backlog grooming for V2 (multi-country, loyalty deep-dive, B2B).

Deliverables: Live production with paying transactions. Runbooks complete.

# 7. Technical Architecture Stack

| Layer | Recommendation | Rationale |
| --- | --- | --- |
| Commerce Engine | ZID Platform (Marketplace plan) | GCC-native, PDPL-compliant, full payment + shipping coverage |
| Backend Framework | Node.js + NestJS (TypeScript) | Type-safe, modular, mature ecosystem |
| API Gateway / BFF | REST + tRPC for internal, GraphQL for mobile aggregation | Channel-tailored payloads |
| Database | PostgreSQL 16 on RDS (multi-AZ) + pgvector | ACID for ledger, embeddings for AI |
| Caching | Redis (ElastiCache) | Hot product cache, OAuth tokens, rate-limit buckets |
| Search | OpenSearch (managed) with Arabic + English analyzers | Catalog search, faceting, RTL tokenization |
| Queue / Events | Amazon SQS + EventBridge | Webhook fan-out, async order processing |
| Object Storage | S3 + CloudFront | KYC documents, gift card assets, signed URLs |
| Cloud Region | AWS me-central-1 (UAE) primary, eu-south-1 DR | PDPL data residency |
| Secrets | AWS Secrets Manager | ZID OAuth tokens, webhook HMAC keys, rotation |
| Observability | Datadog APM + logs + RUM, OpenTelemetry traces | ZID → Haddiya latency visibility |
| Error Tracking | Sentry | Full-stack exception capture |
| Feature Flags | LaunchDarkly or Unleash | Safe rollouts, vendor-segment targeting |
| Data Warehouse | Snowflake or BigQuery + Looker/Metabase | GMV, AOV, cohort, vendor performance |
| CI/CD | GitHub Actions → ECR → ECS Fargate | Blue-green, daily prod deploys |
| IaC | Terraform modules per env | Reproducible infra, drift detection |
| WAF / Security | AWS WAF + Shield | Bot mitigation, DDoS, OWASP top-10 |

# 8. Risk Analysis

## 8.1 Technical & ZID-Specific Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| ZID API rate limits hit during catalog burst sync | Medium | High | Distributed token bucket, exponential backoff, off-peak backfill, request batching |
| Webhook delivery failures / out-of-order events | High | Medium | HMAC verify, idempotency keys, dead-letter queue, periodic reconciliation |
| ZID API contract changes (deprecation, breaking versions) | Medium | High | Pin API version, monitor ZID changelog, integration test suite, abstraction layer |
| Multi-vendor split semantics differ from ZID native model | High | High | Saga pattern, custom mapping table, daily reconciliation |
| OAuth token expiry during high-traffic windows | Low | High | Pre-emptive refresh worker, retry on 401, distributed lock on refresh |

## 8.2 Scalability Concerns

| Concern | Trigger | Mitigation |
| --- | --- | --- |
| ZID API latency spikes under load | GMV spike (Eid, Mother's Day) | Aggressive caching, async order intake, queued writes |
| Webhook backlog during ZID incidents | ZID downtime > 5 min | SQS-backed buffer, replay on recovery, alerting |
| Catalog cache divergence from ZID | Catalog > 50K SKUs across vendors | Hourly reconciliation, drift metrics, alerting on > 0.5% variance |
| Payout ledger reconciliation lag | Daily order volume > 5K | Streaming reconciliation, materialized views, anomaly detection |

## 8.3 Security Risks

| Risk | Severity | Mitigation |
| --- | --- | --- |
| ZID OAuth tokens leaked | Critical | Secrets Manager, no env vars, automated rotation, audit logging |
| Webhook spoofing (forged ZID events) | Critical | HMAC signature verification on every event, replay protection |
| Vendor data cross-tenant leak | High | Tenant scoping in every query, RLS on Postgres, isolation tests |
| PII exposure (Oman PDPL, GDPR) | Critical | Encryption at rest (KMS) + TLS 1.3, field-level PII, audit log, data residency in me-central-1 |
| Supply-chain (npm) attack | Medium | Dependabot, SBOM, Snyk/Socket, signed images, lockfile audit |

## 8.4 Performance Bottlenecks

| Bottleneck | Symptom | Fix |
| --- | --- | --- |
| ZID round-trips on every order page render | Slow product detail | Aggressive Redis cache, read-through from PG mirror |
| N+1 ZID calls during multi-vendor checkout | Slow checkout confirmation | Batch where API supports, parallel fan-out with bulkhead |
| Webhook processing slower than ingestion | Growing SQS backlog | Horizontal worker scale, batch consumption, prioritized queues |
| Reconciliation job blocks DB | Locks during peak | Read replica for recon, off-peak scheduling, chunked queries |

# 9. Final Recommendation

## 9.1 Backend MVP Feature Set

Ship first:

ZID partner app live with OAuth + webhook ingestion.

Catalog sync (products + categories + variants) to Haddiya cache.

Inventory sync (real-time webhooks + reconciliation).

Customer auth bridge (phone+OTP → ZID customer).

Single-vendor cart + checkout, ZID order create, ZID payment (Mada + COD).

Order status webhooks → push notifications to customer.

Basic admin API for order lookup + refund initiation.

Vendor onboarding API (manual approval) + 1 store/vendor.

Send-as-gift v1: message card text stored as order metadata.

Observability baseline (logs + metrics + error tracking).

## 9.2 Defer to V1 / V2

Defer to V1:

Multi-vendor cart splitting (saga + payout ledger).

Gift AI Assistant (LLM + embeddings).

Scheduled delivery slot management.

Loyalty ledger + ZID coupon bridge.

Vendor Portal API (self-service).

Full payment mix (Tabby, Tamara, STC Pay, Apple Pay).

WhatsApp Business notifications.

Reporting pipeline + warehouse.

Defer to V2:

Multi-country expansion (UAE, Bahrain ZID stores) with multi-currency.

B2B corporate gifting API (bulk orders, invoicing, custom branding).

Subscription gifting / recurring deliveries.

Advanced anomaly detection (vendor fraud, inventory anomalies).

Multi-warehouse routing logic.

Marketplace ads / sponsored placement API.

Vendor mobile app backend.

## 9.3 Best Timeline & Milestones

| Milestone | Calendar Week | Outcome |
| --- | --- | --- |
| ZID partner app + OAuth working | W 2 | Sandbox transactions possible |
| Catalog + inventory sync live | W 6 | Cache mirrors ZID in real time |
| Single-vendor checkout end-to-end | W 10 | MVP backend launches private beta |
| Multi-vendor split + payout ledger | W 14 | Marketplace flow functional |
| Gift AI + send-as-gift backend | W 18 | Differentiators live |
| V1 production launch | W 22 | Public consumer launch alongside frontend |
| V2 GCC expansion start | W 26 | Second ZID region onboarded |

## 9.4 Fastest Realistic Approach

Pin ZID API version. Read changelog weekly. Integration test suite runs nightly against sandbox.

Webhook-first, never poll. Polling at scale exhausts rate limits. Reconciliation as safety net only.

Idempotency keys everywhere. Every ZID write carries deterministic external_id derived from Haddiya domain event.

Cache aggressively, invalidate on webhook. Hot products + categories cached in Redis with 15-min TTL + webhook bust.

Saga + dead-letter queues for multi-vendor orders. Partial failures must be observable and replayable.

Daily payout reconciliation in dev from day one. Build the financial truth-table before any vendor ships.

Sandbox-driven development. Every engineer has a personal ZID sandbox; no shared dev env coupling.

Contract tests against ZID API. Pact or schema snapshots catch ZID changes before they reach prod.

Pre-book ZID partner support contact. Direct escalation line for incidents and API questions.

Reserve 15% capacity for ZID quirks. GCC commerce platforms have edge cases — VAT, address formats, name fields.

Bottom line:

A focused backend team of 9–10 FTE delivers production-ready ZID-integrated backend V1 in ~5 months. ZID provides the commerce engine; Haddiya engineers build the marketplace, AI, and gifting differentiators on top. Backend launches alongside the already-completed frontend.

Document prepared for executive review.
API specifications, sprint backlog, and ZID partner contract details available as appendices.